## RAID Log
ARAG Dealer Support Assistant — RAID Log (Risks, Assumptions, Issues, Dependencies, Open Decisions)
Live tracker. The PRD records criteria and mitigation design; this log owns owner, status and target stage. Last reviewed: 8 Oct 2026 (v1.0 release review).
ID | Type | Title | Description | Impact | Likelihood | Severity | Owner | Action / mitigation | Target stage | Status | Links | Last updated
K1 | Issue | Scope inference (O03) | Rule written for two warranty plans applied to a third, with a real citation | High | — | High | Policy Owner; PM + Eng | Now: policy owner defines Essential Plus coverage; O03 kept as regression test. v1.1: answerability check + 5–10 scope questions | Shadow mode | Open | D1; OD1; R1 | 2026-10-08
K2 | Issue | Stale index | Documents changed but chunks or embeddings not refreshed (seen with S16) | High | — | High | Engineering | Now: startup warning (done). v1.1: automatic re-ingest on change; last-updated date on sources | Pilot | In progress | R3; S16 | 2026-10-08
K3 | Issue | Status flips | H03 refused and S05 false conflict in some runs; content correct | Medium | — | Medium | PM + Support Lead | Now: sources shown, feedback, weekly review of refusals/conflicts. v1.1: answerability check; repeat runs per prompt change | Pilot | Open | R6 | 2026-10-08
K4 | Issue | Citation variance | Same answer, different supporting passages across runs | Low | — | Low | Product Manager | Accepted; v1.1 splits decision vs source consistency metrics | Pilot | Accepted | Consistency run | 2026-10-08
K5 | Issue | Evaluation limits | Same-model judge (one false fail); small, builder-written test set | Medium | — | Medium | Product Manager | Now: manual review of judged answers. v1.1: independent 100+ question set; different-model judge | Broad rollout | Open | S03 | 2026-10-08
I6 | Issue | AWS Bedrock access blocked | New AWS account blocked from all Bedrock models pending a support review | Medium | — | Low | Product Manager | Resolved by switching to Azure OpenAI; close AWS support case, deactivate unused key | Shadow mode | Closed | R5 | 2026-10-08
R1 | Risk | Hallucination on unanswerable questions | Model answers from outside knowledge or over-generalizes | High | Medium | High | Product Manager | Grounding prompt, refusal status, code checks on citations; answerability check in v1.1 | Pilot | Materialized → K1 | PRD Risks; K1; O03 | 2026-10-08
R2 | Risk | Misrouting | Question sent to the wrong path (e.g. policy question to the API) | Medium | Low | Medium | Engineering | Tiered router; 100% main and held-out; rules fallback; decider logged per question | Shadow mode | Mitigated | PRD Results; X01–X15 | 2026-10-08
R3 | Risk | Stale knowledge base | Documents change but chunks or embeddings are not refreshed | High | Medium | High | Engineering | Change detection; startup warning; automatic re-ingest in v1.1 | Pilot | Materialized → K2 | K2; S16 | 2026-10-08
R4 | Risk | Data sovereignty | Real dealer data processed outside the UAE | High | Medium | High | Security & Compliance | Synthetic data only in demo; UAE-region hosting and residency review before real data | Pilot | Open | D4 | 2026-10-08
R5 | Risk | Cloud access or quota restrictions | Model access blocked or zero quota on new accounts | High | Medium | Medium | Engineering | Provider-agnostic interface; keyword and rules fallbacks; Pay-As-You-Go with budget alerts | Shadow mode | Materialized → I6 (resolved) | I6 | 2026-10-08
R6 | Risk | LLM non-determinism | Same question gets a different status across runs | Medium | High | Medium | Product Manager | Temperature 0 + seed; repeat-run metric; human review; answerability check v1.1 | Pilot | Materialized → K3 | K3 | 2026-10-08
R7 | Risk | Prompt injection via source documents | Instructions hidden in documents steer the model | High | Low | Medium | Engineering | Passages treated as data in the prompt; ingestion limited to approved documents | Pilot | Mitigated | PRD Risks | 2026-10-08
R8 | Risk | PII exposure in order lookups | Personal data in answers or logs | High | Low | Medium | Security & Compliance | Return only fields agents need; mask personal details in logs | Pilot | Open | D3 | 2026-10-08
R9 | Risk | Live API downtime or slow responses | Inventory or order system unavailable | Medium | Medium | Low | Engineering | 5 s timeout and clear fallback; hybrid still answers policy part; tested | Shadow mode | Mitigated | Failure simulator | 2026-10-08
R10 | Risk | Automation bias | Agents forward answers without checking | High | Medium | High | Support Lead | Mandatory citations; status badges; shadow mode before live use | Shadow mode | Mitigated | A4 | 2026-10-08
R11 | Risk | Conflicting or outdated source documents | Policies contradict each other | Medium | Medium | Medium | Policy Owner | Conflict status shows both sources; policy owner resolves underlying conflicts | Shadow mode | Open | D2; S10; S16 | 2026-10-08
R12 | Risk | LLM cost growth | Usage grows faster than budget | Low | Low | Low | Product Manager | ≈$0.0004/answer; no LLM for real-time; tiered routing; budgets and TPM caps | Broad rollout | Mitigated | PRD Results | 2026-10-08
R13 | Risk | Leaked API key | Key exposed in code or logs | Medium | Low | Low | Engineering | Keys only in secrets; budget alert; rotate in minutes | Shadow mode | Mitigated | — | 2026-10-08
R14 | Risk | Model version retirement | Cloud provider retires the deployed model version | Medium | Medium | Medium | Engineering | Track retirement dates; re-run full evaluation before switching versions | Broad rollout | Open | — | 2026-10-08
D1 | Dependency | Essential Plus coverage definition | Policy owner documents what the plan covers | High | — | High | Policy Owner | Request raised; blocks K1 content fix | Shadow mode | Open | K1; OD1 | 2026-10-08
D2 | Dependency | Return-policy conflicts resolved | Floor mats and special-order part rules contradict | Medium | — | Medium | Policy Owner | Policy owner corrects documents; tests updated | Pilot | Open | R11; OD5 | 2026-10-08
D3 | Dependency | Access to real inventory and order APIs | Production endpoints, credentials, schemas | High | — | High | IT / Platform | Agree integration and test environment | Pilot | Open | A3; R8 | 2026-10-08
D4 | Dependency | UAE-region hosting and residency review | Required before any real dealer data | High | — | High | Security & Compliance | Review and approve hosting region and data handling | Pilot | Open | R4 | 2026-10-08
D5 | Dependency | Support lead for weekly reviews | Owner for refusal/conflict review in shadow mode | Medium | — | Medium | Support Lead | Nominate reviewer and cadence | Shadow mode | Open | K3 | 2026-10-08
OD1 | Decision | Who defines Essential Plus coverage? | Content gap behind K1; model must refuse until defined | High | — | High | Policy Owner | Assign owner and due date | Shadow mode | Open | K1; D1 | 2026-10-08
OD2 | Decision | Does “not listed for a model” mean “not compatible”? | Determines how compatibility answers are phrased to dealers | Medium | — | Medium | Catalog Owner | Decide wording; update prompt rule and S17 | Pilot | Open | S17 | 2026-10-08
OD3 | Decision | Hybrid answer layout | Show live and policy parts separately or blended | Low | — | Low | Product Manager | Decide from shadow-mode feedback | Pilot | Open | — | 2026-10-08
OD4 | Decision | Escalation path for refusals and conflicts | Agents need a defined next step | Medium | — | Medium | Support Lead | Define path and SLA | Shadow mode | Open | K3 | 2026-10-08
OD5 | Decision | Owner and date for resolving audit conflicts | Floor mats and special-order parts | Medium | — | Medium | Policy Owner | Assign owner and due date | Pilot | Open | D2 | 2026-10-08
OD6 | Decision | Knowledge base ownership and update cadence | Who updates documents, how often | High | — | High | Product Manager | Agree owners per document domain | Shadow mode | Open | A5 | 2026-10-08
OD7 | Decision | Refusal target: ≥95% with human review | 100% is unrealistic for LLM-only; needs sign-off | Medium | — | Medium | Product Manager | Approve revised target at release review | Shadow mode | Open | PRD Target Decision | 2026-10-08
A1 | Assumption | Baseline volumes | ~400 queries/week, ~6 min handle time are illustrative | Medium | — | Medium | Product Manager | Validate with real support data during shadow mode | Shadow mode | Open | PRD Problem Statement | 2026-10-08
A2 | Assumption | Test set represents agent phrasing | Questions were written by the builder | Medium | — | Medium | Product Manager | Collect real agent questions in shadow mode; independent test set | Pilot | Open | K5 | 2026-10-08
A3 | Assumption | Mock API matches real systems | Order IDs (ORD-12345), warehouses and fields mirror production | Medium | — | Medium | Engineering | Confirm schemas with system owners before pilot | Pilot | Open | D3 | 2026-10-08
A4 | Assumption | Agents verify cited sources | Agents check citations before replying | High | — | High | Support Lead | Measure in shadow mode; training; status badges | Shadow mode | Open | R10 | 2026-10-08
A5 | Assumption | Knowledge base is authoritative | Documents are current and have owners | High | — | High | Policy Owner | Assign owners and update cadence (OD6) | Shadow mode | Open | OD6 | 2026-10-08
A6 | Assumption | Cost estimates | Token prices are list-price estimates | Low | — | Low | Product Manager | Reconcile with Azure Cost Management monthly | Pilot | Open | R12 | 2026-10-08

## Summary
RAID summary
Counts are formulas over the RAID Log tab and update as statuses change.
Type | Total | Open | In progress | Mitigated / Closed / Accepted | High severity open
Issue | 6 | 3 | 1 | 2 | 1
Risk | 14 | 4 | 0 | 6 | 1
Dependency | 5 | 5 | 0 | 0 | 3
Decision | 7 | 7 | 0 | 0 | 2
Assumption | 6 | 6 | 0 | 0 | 2
Total | 38 | 25 | 1 | 8 | 9
Note: risks that materialized are tracked as issues (e.g. R1 → K1); their risk row shows “Materialized → K…”, counted as neither open nor closed.

## Guide
How to use this log
ID prefixes | K = known issue (from evaluation) · I = other issue · R = risk · A = assumption · D = dependency · OD = open decision
Edit | Update Owner, Action, Target stage and Status in the RAID Log tab; dropdowns are provided. Change Last updated when you edit a row.
Status values | Open · In progress · Mitigated · Closed · Accepted · Materialized → K… (a risk that became an issue)
Severity | Rated by impact on the dealer (wrong information reaching a dealer = High), not by frequency in metrics
Target stage | The rollout stage whose release gate requires the item: Shadow mode · Pilot · Broad rollout (see PRD > Release Gates)
Review cadence | Weekly during shadow mode and pilot; at every release review
Example row | K1 ¦ Issue ¦ Scope inference (O03) ¦ … ¦ Policy Owner; PM + Eng ¦ … ¦ Shadow mode ¦ Open
Related documents | PRD (docs/ARAG_Model_PRD.docx) · v1.0 Release Review (docs/ARAG_v1.0_Release_Review.docx)