# ARAG v1.0: Release Review & Retrospective

Dealer Support Assistant — milestone review, go/no-go for shadow mode

| Field | Detail |
| --- | --- |
| Milestone | v1.0 — offline build and evaluation complete (rollout stage 1) |
| Review date | 8 October 2026 |
| Period | 2–8 October 2026 |
| Author | [Your Name], Product Manager |
| Decision requested | Go / no-go for rollout stage 2 (shadow mode) |
| Related documents | PRD v2.3 (docs/ARAG_Model_PRD.docx) · RAID log (docs/ARAG_RAID_Log.xlsx) · CHANGELOG.md |

# Summary and Recommendation

v1.0 delivers the full planned scope: an assistant that answers dealer support questions from policy documents and live systems, with cited answers, explained routing and graceful fallbacks. It meets 5 of the 7 quality targets that can be measured offline (routing counted once). The two misses (refusal correctness and consistency) are labeling and stability issues rather than wrong facts, with one important exception (K1, below).

Recommendation: conditional go for shadow mode. 1 of 4 entry gates is met. Enter shadow mode once the remaining three are complete; none requires new engineering, but one depends on the policy owner (D1).

| Shadow-mode gate | Status | Note |
| --- | --- | --- |
| K1 content fixed (Essential Plus coverage defined) | Not met | Depends on D1 / OD1 |
| K2 stale-index warning live | Met | Startup warning shipped |
| Zero confident-wrong answers across 3 runs | Not met | O03 fails consistently until K1 content fix |
| Manual review of judged answers | Not met | ≈10 minutes; to do before sign-off |

Decisions requested at this review: (1) approve the conditional go; (2) approve the revised refusal target, ≥95% with human review of every refusal and conflict (OD7); (3) assign owners for OD1 (Essential Plus coverage) and OD6 (knowledge base ownership).

# Scope: Planned vs Delivered

| Planned (PRD in-scope) | Delivered | Notes |
| --- | --- | --- |
| Static knowledge Q&A via RAG | ✅ | Vector search; cited answers with answered / refused / conflict status |
| Real-time Q&A (stock, orders) | ✅ | Template answers, no LLM, exact numbers; mock APIs with failure simulation |
| Routing incl. hybrid queries | ✅ | Tiered router (rules fast path + LLM intent + rules fallback) |
| Clarification for missing IDs | ✅ | Plus follow-up resolution: “BRK-1020”, “the left one”, “10482” |
| Source citations | ✅ | 100% coverage; invalid citations dropped in code |
| Hallucination guardrails | ✅ partial | Refusals and conflict flags work; scope inference remains (K1) |
| Logging and feedback | ✅ | Route, decider, sources, status, tokens, latency; 👍/👎 |

Delivered beyond plan: rules / LLM / tiered router comparison with cost tracking; three-way retrieval comparison; answer evaluation with an LLM judge and repeat-run consistency; stale-index warning; 167 automated tests that never call the cloud.

Deferred, with reason: answerability check, automatic re-ingest and an independent test set (v1.1, mitigations for K1–K5); public demo deployment (optional); handle-time measurement (needs real agents, shadow mode); multi-turn memory (out of scope by design, v2).

# Results vs Targets

| Metric | Target | v1.0 | Status |
| --- | --- | --- | --- |
| Retrieval relevance (doc hit@3) | ≥80% | 100% (vector, 22 queries) | Met |
| Routing accuracy, main / held-out | ≥90% | 100% (42/42) / 100% (15/15); rules 80% held-out | Met |
| Answer correctness | ≥85% | 96% (LLM-judged) | Met |
| Citation coverage | 100% | 100% | Met |
| Conflicts flagged | — | 2 / 2 | Met |
| Latency p90 | <5 s | 2.9–3.2 s | Met |
| Cost per answered question | — | ≈ $0.0004 | — |
| Refusal correctness | 100% | 93–97% across runs | Below (K1, K3) |
| Consistency (same question, 3 runs) | ≥95% | 90% (26/29) | Below (K3, K4) |
| Handle time reduction | ≥30% | Not measurable offline | Shadow mode |

Full detail: PRD > Results & Learnings.

# Key Decisions and Pivots

| Decision | Planned | Final | Evidence |
| --- | --- | --- | --- |
| Cloud provider | AWS Bedrock | Azure OpenAI | New AWS account blocked from all models; switch needed no code rework |
| Retrieval | Hybrid (BM25 + vector) | Vector; hybrid configurable | Vector 100% vs hybrid 91% chunk hit@3 |
| Routing | LLM classifier | Tiered (rules + LLM) | Same 100% accuracy as LLM-only with 25% fewer LLM calls |
| Real-time answers | LLM phrasing | Templates, no LLM | Exact numbers; lower cost and risk |
| Prompt tuning | Fix each miss with a rule | Stopped; structural fix planned | Each rule moved a miss elsewhere |

# Open Items Handed Over

All items have an owner and a target stage in the RAID log (38 items: 6 issues, 14 risks, 6 assumptions, 5 dependencies, 7 open decisions). Highest priority:

| ID | Item | Owner | Target stage | Status |
| --- | --- | --- | --- | --- |
| K1 | Scope inference (O03) | Policy Owner; PM + Eng | Shadow mode | Open |
| K2 | Stale index | Engineering | Pilot | In progress |
| K3 | Status flips | PM + Support Lead | Pilot | Open |
| K4 | Citation variance | Product Manager | Pilot | Accepted |
| K5 | Evaluation limits | Product Manager | Broad rollout | Open |
| D1 | Essential Plus coverage definition | Policy Owner | Shadow mode | Open |
| D3 | Access to real inventory and order APIs | IT / Platform | Pilot | Open |
| D4 | UAE-region hosting and residency review | Security & Compliance | Pilot | Open |
| OD1 | Who defines Essential Plus coverage? | Policy Owner | Shadow mode | Open |
| OD6 | Knowledge base ownership and update cadence | Product Manager | Shadow mode | Open |
| OD7 | Refusal target: ≥95% with human review | Product Manager | Shadow mode | Open |

# Cost and Effort

| Item | v1.0 |
| --- | --- |
| Model usage (embeddings, answers, routing, all evaluation runs) | Well under $1 (estimate; confirm in Azure Cost Management) |
| Infrastructure | $0: GitHub Codespaces free tier; mock APIs and app run in the codespace |
| Cost per answered question (production estimate) | ≈ $0.0004, plus ≈ $0.0002 per LLM routing call |
| Elapsed time | About one week (2–8 October 2026), including cloud setup |
| Unplanned effort | AWS account access (several days blocked); Azure trial quota; prompt-tuning iterations |
| Quality assets | 167 automated tests; 42-question test set; 15-question held-out set; RAID log |

# Retrospective

## What went well

- Evaluation first. Writing the test set before building turned every decision into a measurement and caught problems a demo would have hidden.

- Local-first, zero-cost build. The whole pipeline was built and tested without an LLM, so the cloud phase only added models to a working system.

- Held-out set. It exposed the rule router's overfitting (100% vs 80%) and made the LLM router's value measurable.

- Provider-agnostic design. Switching from AWS to Azure was a configuration change.

- Content audit. It predicted the hardest failures (the Essential Plus gap, two policy conflicts) before any code existed.

## What didn't go well

- Cloud access. Bedrock was blocked for days on a new AWS account; Azure free trials have zero model quota.

- Prompt-tuning whack-a-mole. Three rounds of prompt rules moved misses around rather than removing them.

- Self-inflicted stale index. A test edit to a policy document was reverted, but the index wasn't rebuilt, so the assistant kept serving the old text.

- Manual code handover. Moving code by zip files instead of pull requests was error-prone and made changes harder to review.

## What I'd do differently

- Verify model access on day one, before designing around a provider.

- Version the test set's expected answers with the knowledge base, and automate re-ingest from the start.

- Set a stop rule for prompt tuning: at most two iterations, each validated on questions not used to tune it.

- Give each LLM call one narrow decision from the start (as the router does), rather than one prompt doing everything.

- Use a pull-request workflow from the first commit.

# Next Steps

| When | Action | Owner |
| --- | --- | --- |
| Before shadow mode | Policy owner defines Essential Plus coverage (D1); re-run evaluation 3 times with zero confident-wrong answers | Policy Owner; PM |
| Before shadow mode | Manual review of judged answers; nominate weekly reviewer (D5); define escalation path (OD4) | PM; Support Lead |
| Before shadow mode | Close AWS support case; deactivate unused AWS access key (I6) | PM |
| v1.1 (before pilot) | Answerability check; automatic re-ingest; independent 100+ question test set; different-model judge | PM + Eng |
| Before pilot | Real API access (D3); UAE-region hosting and data residency review (D4) | IT / Platform; Security |

# Sign-off

| Role | Name | Decision | Date |
| --- | --- | --- | --- |
| Product Manager | [Your Name] | Conditional go | [date] |
| Engineering lead | [name] |  |  |
| Support lead | [name] |  |  |
| Policy owner | [name] |  |  |

Portfolio note: this review uses synthetic data and fictional roles; it demonstrates the milestone governance a product of this kind would need.